## EVM Calculator
EVM CALCULATOR
Project Budget | 4000 | Change only the blue cells!
Project Start | 2025-01-14
Project End | 2029-01-14
Total Spent | 1500
Work Completed | 35%
Current Date | 2026-06-14 | Find more at: https://egecangun.com
Project Duration | 4 Years, 0 Months, 0 Days
% Done | 35.32%
Budget at Completion [BAC] | 4000
Actual Cost [AC] | 1500
Planned Value [PV] | 1412.731
Earned Value [EV] | 1400
Cost Variance [CV] | -100 | Over Budget
Cost Performance Index [CPI] | 93.33%
Schedule Variance [SV] | -12.731 | Behind Schedule
Schedule Performance Index [SPI] | 99.1%
Estimate at Completion [EAC] | 4285.7143 | Team Should Work 0,04 more efficiently
Estimate to Completion [ETC] | 2785.7143
Variance at Completion [VAC] | -285.7143
To-Complete Performance Index [TCPI] | 104%